## Read Me
HIVE Knowledge Preprocessing Pipeline – INT Incremental Update Test Runbook
Purpose | Step-by-step execution guide for the 16 incremental-update scenarios (Confluence: 'Incremental Update Integration Scenario Tests'). Anyone with the access below can run it: change content in Athena, trigger the pipeline, run the SQL in Spanner Studio, check GCS, record the result.
Owner | Vamsi (QA). Prepared 29 Sep 2026. Validate against the build deployed to INT; see sheet 'Pre-flight' before starting.
1. Environment
Athena (INT) | https://lloyds-banking-test.eu1prod.expert.nicecxone.com → Customer Vulnerability Hub 2 › Vulnerabilities › Test Area (page_id 43599)
Tracked root | 39960 = Customer Vulnerability Hub 2 (the Test Area sits under this root)
GCP project | wrk-int-wrk01-svp-dfadf4
Spanner instance / DB | ew2-int-wrk01-spi-ka-spanner / hive-int-context-layer-db
Spanner Studio URL | https://console.cloud.google.com/spanner/instances/ew2-int-wrk01-spi-ka-spanner/databases/hive-int-context-layer-db/details/query?project=wrk-int-wrk01-svp-dfadf4
GCS buckets | HTML: <HTML_BUCKET> JSON: <JSON_BUCKET> MD: <MD_BUCKET> (fill in during Pre-flight PF-6)
GCS object path | <FOLDER>/<page_id>/metadata.json (JSON bucket) · <FOLDER>/<page_id>/page.md (MD bucket) · <FOLDER>/<page_id>/page.html (HTML bucket). <FOLDER> is recorded in PF-6.
Job API (INT) | <INT_BASE_URL> (Bruno collection: initial-job.bru, incremental-job.bru, job-status.bru). Confirm with dev in PF-1.
2. Golden rules
Rule 1 | Only edit pages listed on sheet 'Page Register'. Never edit real content pages. Never touch 'QE' / 'Sanity Tests'.
Rule 2 | Run scenarios strictly in the order of the 'Seq' column on sheet 'Test Cases'. Later scenarios depend on earlier ones (deletes and moves are last).
Rule 3 | One scenario at a time. Do not make any other Athena edit in the Test Area until the scenario's checks are finished.
Rule 4 | ALWAYS record T0 (CC-1) immediately before the Athena change. All 'after' queries filter on ingested_at > T0.
Rule 5 | Where a scenario says BEFORE, run that query and Export the result BEFORE touching Athena – it is your baseline for comparison.
Rule 6 | Summary/intents are LLM-generated: check they are present and sensible, NOT that the wording is identical between runs.
3. How to run a query in Spanner Studio
Steps | 1) Open the Spanner Studio URL. 2) Click '+ New SQL Editor Tab'. 3) Paste the query. 4) Replace every <PLACEHOLDER> (e.g. <T0>, <CHILD_C_ID>) with the real value from 'Run Log' / 'Page Register'. 5) Highlight ONLY that query and click 'Run selected'. 6) Evidence: Results → Export → CSV, named <CaseID>_<QueryLetter>_<before¦after>.csv (e.g. S02_a_after.csv), or take a screenshot.
Timestamps | Spanner stores UTC. Get T0 with CC-1 (SELECT CURRENT_TIMESTAMP()) and paste the exact value, e.g. TIMESTAMP('2026-10-01T09:15:02.123456Z').
4. How to check GCS
Steps | Console → Cloud Storage → Buckets → open bucket → in 'Filter by name prefix' type <FOLDER>/<page_id>/ → the object list shows Name, Size, 'Last modified/Updated'. Click an object → 'Object details' shows the crc32c/MD5 hash (use to prove a file is byte-identical). Use 'Download' to open metadata.json / page.md.
5. Trigger procedure (TP) – used in every scenario
Option A – Bruno (preferred) | incremental-job.bru → POST <INT_BASE_URL>/api/v1/jobs/incremental → copy job_id from the response → job-status.bru → GET <INT_BASE_URL>/api/v1/jobs/<job_id> every ~1 min until status = SUCCESS. If FAILED: screenshot the response, stop, log a defect.
Option B – Scheduler | Wait for the next scheduled run (every 30 min). Allow up to 35 min.
Confirm the run (both options) | Run CC-2. Continue only when a new row for root 39960 with ingested_at > T0 and status COMPLETED exists. NOTE: the scheduler may process your change before you trigger manually – that is fine; the checks find whichever run processed it.
6. Status values
Pass | All 'What to verify' criteria met.
Pass with observation | Criteria met but something unexpected worth noting (log it on 'Defects & Observations').
Fail | Any criterion not met → log on 'Defects & Observations' with the query result as evidence.
Blocked | Could not execute (e.g. pipeline down, no dev support for S09). Write the reason in Notes.
7. Sheets in this workbook
Pre-flight | Checks to run once, before any scenario. If any STOP condition is hit, do not start testing.
Page Register | The test pages: their IDs, the exact content to paste in Athena, and links to add. Fill the yellow cells.
Common Checks | Reusable queries (CC-1 … CC-8) referenced from the test cases.
Test Cases | The 3 setup steps + 16 scenarios, in execution order. Fill the yellow columns.
Run Log | One row per execution: T0, trigger, job IDs, Athena revisions.
Defects & Observations | Pre-filled with findings from discovery on 29 Sep 2026; add new ones here.
Summary | Auto-counts results from 'Test Cases'.

## Pre-flight
ID | Check | How / Query | Expected | STOP if… | Actual | OK? (Y/N)
PF-1 | Dev confirms readiness | Ask dev: (1) which build/commit is deployed to INT, (2) Liquibase migration applied to hive-int-context-layer-db, (3) is the 30-min scheduler ON or OFF, (4) <INT_BASE_URL> for the job APIs, (5) who can induce a controlled failure for S09. | All 5 answered. Record in Read Me / Run Log. | Dev has not confirmed deployment.
PF-2 | Application tables exist | SELECT table_name FROM information_schema.tables WHERE table_schema = '' ORDER BY table_name; | Includes: job, page, page_audit, page_dependency, page_since (plus DATABASECHANGELOG*). | 'job' missing (it was missing on 29-Sep → schema not migrated).
PF-3 | Columns match the current code | SELECT table_name, column_name FROM information_schema.columns WHERE (table_name = 'page_audit' AND column_name IN ('job_type','load_type','status','has_errors','error_details')) OR (table_name = 'page' AND column_name IN ('draft_state','summary','primary_intents','confidence_score','source_object_name')) ORDER BY table_name, column_name; | Exactly 10 rows. | Fewer than 10 rows (on 29-Sep page_audit.job_type was missing and page had is_draft instead of draft_state).
PF-4 | Knowledge graph exists | SELECT property_graph_name FROM information_schema.property_graphs; | knowledge_graph | No row.
PF-5 | Pipeline is alive | SELECT page_id, job_run_id, status, since_time, watermark_time, ingested_at FROM page_since WHERE page_id = '39960' ORDER BY ingested_at DESC LIMIT 5; | A COMPLETED row after the deployment date (trigger once with TP if needed). | Latest row is older than the deployment (last seen 18-Sep-2026).
PF-6 | GCS access + folder name | Console → Cloud Storage → Buckets. Note the 3 bucket names (HTML / JSON / MD). Open the JSON bucket and note the top-level folder = <FOLDER>. Filter <FOLDER>/43609/ – confirm metadata.json is visible and downloadable. | 3 bucket names + <FOLDER> recorded in Read Me. | No access to any bucket.
PF-7 | Athena permissions | In Athena Test Area confirm you can: create a page, edit, move (Options → Move), delete, and restore an older revision (Page history). | All 5 possible. | Cannot delete/move/restore → mark S05, S08, S10, S14 Blocked (or get a content admin).
PF-8 | Spanner audit table is being written | SELECT load_type, status, COUNT(*) AS n FROM page_audit GROUP BY load_type, status ORDER BY 1, 2; | Rows exist after the first post-deployment run (table was EMPTY on 29-Sep). | Still empty after a successful run → log defect (audit not written).

## Page Register
Page title | Location (parent) | page_id | Action in SU-2 | Body content to paste (exactly) | Links to add (link text → target page) | Used in | Notes
Test Area | Vulnerabilities | 43599 | No change | (leave as is) | (subpage links are automatic) | All | Root of the test area.
Parent A | Test Area | 43601 | Edit body | QA-ZX91 Parent A. Test content for preprocessing pipeline testing only – not real guidance. ## Overview This section groups QA test pages for the incremental update tests. | 'Child AA' → Child AA 'Link target' → QA Link Target S14 | S04, S10, S14 | Navigation page.
Parent B | Test Area | 43603 | Edit body | QA-ZX91 Parent B. Test content for preprocessing pipeline testing only – not real guidance. ## Overview This section holds the child pages used for update tests. | 'Child B' → Child B | S08, S10, S15
Child AA | Parent B | 43609 | Edit body | QA-ZX91 Child AA procedure. Test content only – not real guidance. ## Step 1 The colleague opens the QA test record and checks the reference. ## Step 2 The colleague follows the next steps described in Child B and Child C. | 'Child B' → Child B 'Child C' → Child C 'External Support' → External Support (real page) 'Example site' → https://example.com/qa-zx91 | S02, S03, S04 | Spanner (29-Sep) still shows it under Parent_A – SU-3 verifies it moves to Parent_B.
Child B | Parent B | 43607 | Edit body | QA-ZX91 Child B reference. Test content only – not real guidance. ## Details Reference information for the QA test record. | (none) | S06, S09, S11, S16
Child C | Parent B | <CHILD_C_ID> | Edit body | QA-ZX91 Child C reference. Test content only – not real guidance. ## Details Additional reference information for the QA test record. | 'Child B' → Child B | S07, S10 | Not yet in Spanner on 29-Sep. Get ID in SU-3.
QA Delete Me S5 | Parent A | <S5_ID> | CREATE | QA-ZX91 page to be deleted in scenario S5. Test content only. ## Details This page will be removed. | (none) | S05
QA Link Target S14 | Parent A | <S14_ID> | CREATE | QA-ZX91 link target – will be deleted in scenario S14. Test content only. ## Details This page is linked from Parent A. | (none) | S14 | Parent A links TO this page.
QA Multi-Link S15 | Parent A | <S15_ID> | CREATE | QA-ZX91 multi-dependency test page. Test content only. ## Related pages See the linked pages below. | 'Child AA' → Child AA 'Child B' → Child B 'Child C' → Child C | S15
QA New Page S1 | Parent A | <S1_ID> | Do NOT create in SU-2 (created during S01) | QA-ZX91 New Page S1. Test content only – not real guidance. ## Overview This page was created to test new-page detection. | 'Child B' → Child B | S01
External Support (REAL page) | Vulnerabilities | <REAL_ID> | READ ONLY – never edit | (real content – do not edit) | - | Link target | ID from SU-3 query (d).
Child A | (in Spanner under Parent_A) | 43605 | Do not recreate | - | - | SU-3 | In Spanner (29-Sep) but not visible in Athena – SU-3 checks it is removed if deleted.
QE / Sanity Tests | Test Area | - | DO NOT TOUCH | - | - | - | Owned by someone else / out of scope.

## Common Checks
ID | Purpose | Query | Expected / how to read
CC-1 | Record T0 (start time, UTC) | SELECT CURRENT_TIMESTAMP() AS t0; | Copy the value into Run Log → T0. Use it as <T0> in the scenario queries.
CC-2 | Confirm a pipeline run happened after T0 | SELECT page_id, job_run_id, status, since_time, watermark_time, ingested_at FROM page_since WHERE page_id = '39960' AND ingested_at > TIMESTAMP('<T0>') ORDER BY ingested_at DESC; | ≥ 1 row, status = COMPLETED. Copy job_run_id into Run Log. 0 rows = run not finished yet (wait / re-trigger).
CC-3 | Snapshot of all Test Area pages | SELECT page_id, title, page_type, revision, path, content_size, date_modified, ingested_at FROM page WHERE path LIKE 'Customer_Vulnerability_Hub_2/Vulnerabilities/Test_Area%' ORDER BY path; | Use for before/after comparisons. Export as CSV.
CC-4 | Snapshot of all Test Area links | SELECT d.page_id, d.dependency_page_id, d.type, d.relationship_label, d.relationship_confidence, d.is_broken, d.href FROM page_dependency d JOIN page p ON p.page_id = d.page_id WHERE p.path LIKE 'Customer_Vulnerability_Hub_2/Vulnerabilities/Test_Area%' ORDER BY d.page_id, d.dependency_page_id; | Use for before/after comparisons. External links point to dependency_page_id = '00000'.
CC-5 | Audit rows since T0 (Test Area) | SELECT a.page_id, a.job_run_id, a.job_type, a.load_type, a.status, a.has_errors, a.error_details, a.revision, a.ingested_at FROM page_audit a WHERE a.page_id IN (SELECT page_id FROM page WHERE path LIKE 'Customer_Vulnerability_Hub_2/Vulnerabilities/Test_Area%') AND a.ingested_at > TIMESTAMP('<T0>') ORDER BY a.ingested_at; | Changed pages show status 'completed' (possibly after 'in_progress'). No 'failed' unless the scenario expects it. NOTE: deleted pages are not in 'page' – query their page_id directly.
CC-6 | Dangling links (target page does not exist) | SELECT d.page_id, d.dependency_page_id, d.type, d.is_broken, d.href FROM page_dependency d LEFT JOIN page t ON t.page_id = d.dependency_page_id WHERE d.page_id IN (SELECT page_id FROM page WHERE path LIKE 'Customer_Vulnerability_Hub_2/Vulnerabilities/Test_Area%') AND t.page_id IS NULL; | 0 rows. Any row must at least have is_broken = TRUE, otherwise it is a stale relationship → defect.
CC-7 | Duplicate links | SELECT d.page_id, d.dependency_page_id, d.type, COUNT(*) AS n FROM page_dependency d WHERE d.page_id IN (SELECT page_id FROM page WHERE path LIKE 'Customer_Vulnerability_Hub_2/Vulnerabilities/Test_Area%') GROUP BY d.page_id, d.dependency_page_id, d.type HAVING COUNT(*) > 1; | 0 rows. If rows appear, compare href: the same target linked from two different sections is allowed; identical duplicates are a defect.
CC-8 | Graph view agrees with the tables (optional) | GRAPH knowledge_graph MATCH (p:Page)-[d:DependsOn]->(t:Page) WHERE p.page_id = '<PAGE_ID>' RETURN t.page_id, t.title, d.type, d.relationship_label; | Same targets as the page_dependency query for that page.

## Test Cases
Seq | Case ID | Scenario (what & why) | Athena action – step by step | What is tested (expected outcome) | Queries to execute (Spanner Studio) | What to verify (pass criteria per query) | GCS check | Actual result | Status | Evidence (file names) | Known risk / dev note
1 | SU-1 | Pre-flight (once) | Run every check on sheet 'Pre-flight'. | Environment is ready: new build deployed, schema migrated, pipeline running, access OK. | See sheet 'Pre-flight' (PF-1 … PF-8). | All PF checks OK. Any STOP condition → do not continue; report to dev. | PF-6 |  | Not run
2 | SU-2 | Build the test content in Athena (once) | 1. Run CC-1, record T0 in Run Log (row SU-2). 2. Open Test Area. Confirm the tree: Parent A; Parent B → Child AA, Child B, Child C. 3. For each page on 'Page Register' with Action 'Edit body': Edit → replace body with the text given → add the links given (use Athena's link tool for internal pages) → Save/Publish. 4. Create the 3 pages marked CREATE under Parent A (New → page), paste body + links → Publish. 5. Add the Parent A links last (they point to QA Link Target S14). 6. Do NOT create 'QA New Page S1' yet. Do not touch QE / Sanity Tests. | Content ready for all scenarios. | (none – Athena only) | All pages on 'Page Register' exist in Athena with the exact content and links. | - |  | Not run
3 | SU-3 | Baseline run + snapshot (once) | 1. No Athena changes. 2. Trigger (Read Me §5) and wait for CC-2 to show a COMPLETED run after the SU-2 T0. | Pipeline picks up everything done in SU-2 and the earlier Athena changes (Child AA moved to Parent B, Child C / new pages created, Child A removed). This baseline is what every scenario compares against. | (a) CC-2 with T0 from SU-2. (b) Page IDs: SELECT page_id, title, page_type, revision, path, summary IS NOT NULL AS has_summary, ingested_at FROM page WHERE path LIKE 'Customer_Vulnerability_Hub_2/Vulnerabilities/Test_Area%' ORDER BY path; (c) CC-4 (links snapshot). (d) Real link target ID: SELECT page_id, title, path FROM page WHERE title = 'External Support' AND path LIKE 'Customer_Vulnerability_Hub_2%'; (e) Is Child A gone? SELECT page_id, title, path FROM page WHERE page_id = '43605'; (f) CC-6 and CC-7. | (a) COMPLETED run. (b) One row per Page Register page (except QA New Page S1). Child AA path ends /Parent_B/Child_AA; Child C, QA Delete Me S5, QA Link Target S14, QA Multi-Link S15 present; has_summary = true for all non-navigation pages. → Copy IDs into Page Register (yellow cells). (c) Links as per Page Register, plus type 'subpage' rows parent → child. Export as SU3_links_baseline.csv. (d) Copy page_id into Page Register <REAL_ID>. (e) 0 rows if Child A was deleted in Athena (if still present → log observation: deleted page not purged). (f) 0 rows. Export (b) as SU3_pages_baseline.csv. | For 43609 and each new page: metadata.json, page.md, page.html exist under <FOLDER>/<page_id>/. |  | Not run |  | This first run already exercises S01 (new pages), S05 (Child A delete) and S10 (Child AA move). Record any mismatch.
4 | S12 | Pipeline triggered when there are NO Athena changes | 1. Make NO changes in Athena. 2. Run CC-1 → T0. 3. Trigger (TP) and confirm with CC-2. | Nothing in the Test Area is reprocessed: no page/link changes, no duplicates, GCS untouched, watermark still advances. | (a) CC-2. (b) SELECT page_id, revision, ingested_at FROM page WHERE path LIKE 'Customer_Vulnerability_Hub_2/Vulnerabilities/Test_Area%' AND ingested_at > TIMESTAMP('<T0>'); (c) CC-5. (d) CC-7. | (a) ≥1 COMPLETED row (run happened, nothing to do). (b) 0 rows. (c) 0 rows. (d) 0 rows. | Child AA (43609) objects: 'Updated' time is BEFORE T0. |  | Not run
5 | S13 | Same page processed repeatedly (idempotency) | 1. No Athena changes. 2. CC-1 → T0. 3. Trigger incremental again (2nd consecutive no-change run). 4. OPTIONAL, only with dev approval: force reprocessing of the root via initial-job.bru with body {"root_page_ids": ["39960"]} (re-tags ALL Hub 2 pages – cost/time). | Repeated processing leaves identical state: one row per page, same link set, no extra GCS files, metadata still valid. | (a) SELECT page_id, COUNT(*) AS n FROM page WHERE path LIKE 'Customer_Vulnerability_Hub_2/Vulnerabilities/Test_Area%' GROUP BY page_id HAVING COUNT(*) > 1; (b) SELECT d.page_id, COUNT(*) AS links FROM page_dependency d JOIN page p ON p.page_id = d.page_id WHERE p.path LIKE 'Customer_Vulnerability_Hub_2/Vulnerabilities/Test_Area%' GROUP BY d.page_id ORDER BY d.page_id; (c) CC-7. (d) SELECT page_id, title, revision, summary IS NOT NULL AS has_summary, ARRAY_LENGTH(primary_intents) AS n_intents, confidence_score FROM page WHERE path LIKE 'Customer_Vulnerability_Hub_2/Vulnerabilities/Test_Area%' ORDER BY page_id; | (a) 0 rows. (b) Link count per page = SU-3 baseline (SU3_links_baseline.csv). (c) 0 rows. (d) Revisions = baseline; has_summary true; confidence_score between 0 and 1. If step 4 was run, summary wording may differ slightly (LLM) – NOT a defect; empty/NULL is. | Each Test Area page folder contains exactly 3 objects (metadata.json, page.md, page.html) – no extra/old files. |  | Not run
6 | S11 | No-op change (revision ≤ stored revision) | 1. CC-1 → T0. 2. Open Child B → Page history: note current revision R0 (Run Log). 3. Edit → Save WITHOUT changing anything. 4. Page history again: note if a new revision R1 was created (Run Log). 5. Trigger (TP). | If Athena did not create a new revision, the pipeline does nothing for Child B. | (a) SELECT page_id, revision, content_size, ingested_at FROM page WHERE page_id = '43607'; (b) SELECT page_id, job_run_id, job_type, load_type, status, has_errors, error_details, revision, ingested_at FROM page_audit WHERE page_id IN ('43607') AND ingested_at > TIMESTAMP('<T0>') ORDER BY ingested_at; | If NO new Athena revision: (a) revision = R0 and ingested_at < T0; (b) 0 rows → PASS. If Athena DID create R1: pipeline is expected to reprocess ((a) revision = R1, (b) 'completed' rows) → 'Pass with observation: Athena bumps revision on a no-change save'. Anything else (e.g. failed rows) → FAIL. | Child B objects: Updated before T0 (no new revision case). |  | Not run |  | Code skips a page when stored revision ≥ Athena revision.
7 | S01 | New page created under a tracked root | 1. CC-1 → T0. 2. Parent A → New → page. Title: QA New Page S1. 3. Paste body from Page Register; add link 'Child B' → Child B. Publish. 4. Note its page_id (Athena page info, or query (a)) in Page Register <S1_ID>. 5. Trigger (TP). | Detected as new, fetched, tagged; new page row; metadata populated; link rows incl. parent (subpage) link; 3 GCS files; audit rows. | (a) SELECT page_id, title, page_type, revision, path, content_size, deleted, unpublished, summary, ARRAY_LENGTH(primary_intents) AS n_intents, confidence_score, source_object_name, ingested_at FROM page WHERE title = 'QA New Page S1'; (b) SELECT page_id, dependency_page_id, type, relationship_label, relationship_confidence, is_broken, href FROM page_dependency WHERE page_id = '<S1_ID>' OR dependency_page_id = '<S1_ID>'; (c) SELECT page_id, job_run_id, job_type, load_type, status, has_errors, error_details, revision, ingested_at FROM page_audit WHERE page_id IN ('<S1_ID>', '43601') AND ingested_at > TIMESTAMP('<T0>') ORDER BY ingested_at; (d) CC-2. | (a) Exactly 1 row; path ends /Test_Area/Parent_A/QA_New_Page_S1 (or Athena's URL for it); revision = Athena revision; summary not empty; n_intents ≥ 1; 0 ≤ confidence_score ≤ 1; deleted = false; unpublished = false; ingested_at > T0. (b) Row <S1_ID> → 43607, type 'internal', relationship_label one of: escalation, next_step, prerequisite, conditional_guidance, procedural_guidance; confidence 0–1; is_broken = false. Row 43601 → <S1_ID>, type 'subpage'. (c) 'completed' rows for <S1_ID>; no 'failed'. (d) New COMPLETED row. | JSON: <FOLDER>/<S1_ID>/metadata.json · MD: <FOLDER>/<S1_ID>/page.md · HTML: <FOLDER>/<S1_ID>/page.html all exist. Download metadata.json → title = 'QA New Page S1'. |  | Not run |  | 'Local output_{page_id} files' in Confluence = local run only; N/A on INT.
8 | S02 | Existing page content updated (body text changed) | 1. BEFORE: run query (a), export S02_a_before.csv. 2. CC-1 → T0. 3. Edit Child AA → change the 'Step 1' sentence to: QA-ZX91 Step 1 UPDATED for S2: the colleague must record the test reference number. Save/Publish. Note new Athena revision. 4. Trigger (TP). | Same row upserted (no duplicate); content_size, revision, date_modified changed; tags/summary refreshed; GCS files overwritten; audit entry. | (a) SELECT page_id, title, revision, content_size, date_modified, summary, primary_intents, ingested_at FROM page WHERE page_id = '43609'; (b) SELECT COUNT(*) AS n FROM page WHERE page_id = '43609'; (c) SELECT dependency_page_id, type, relationship_label FROM page_dependency WHERE page_id = '43609' ORDER BY dependency_page_id; (d) SELECT page_id, job_run_id, job_type, load_type, status, has_errors, error_details, revision, ingested_at FROM page_audit WHERE page_id IN ('43609') AND ingested_at > TIMESTAMP('<T0>') ORDER BY ingested_at; | (a) vs before: revision higher (= Athena); content_size different; date_modified newer; summary present (refreshed); ingested_at > T0. (b) n = 1. (c) Same targets as in SU-3 baseline for 43609 (Child B, Child C, External Support, '00000'). (d) 'completed'; no 'failed'. | 43609 page.md and metadata.json 'Updated' after T0; download page.md → contains 'UPDATED for S2'. |  | Not run
9 | S03 | Existing page updated – a link removed | 1. BEFORE: run (a), export S03_a_before.csv. 2. CC-1 → T0. 3. Edit Child AA → delete the 'Child C' link (and its text). Save/Publish. 4. Trigger (TP). | Page updated; the removed link's page_dependency row is GONE; metadata.json no longer lists it. | (a) SELECT dependency_page_id, type, relationship_label, href, is_broken FROM page_dependency WHERE page_id = '43609' ORDER BY dependency_page_id; (b) SELECT COUNT(*) AS stale FROM page_dependency WHERE page_id = '43609' AND dependency_page_id = '<CHILD_C_ID>'; (c) SELECT revision, ingested_at FROM page WHERE page_id = '43609'; (d) SELECT page_id, job_run_id, job_type, load_type, status, has_errors, error_details, revision, ingested_at FROM page_audit WHERE page_id IN ('43609') AND ingested_at > TIMESTAMP('<T0>') ORDER BY ingested_at; | (a) Still contains Child B, External Support, '00000'; no Child C. (b) stale = 0. If 1 → FAIL: stale dependency (known risk). (c) revision higher; ingested_at > T0. (d) 'completed'. | 43609 metadata.json Updated after T0; search it for '<CHILD_C_ID>' → not in relationship list. |  | Not run |  | Known risk: link PK = (page_id, dependency_page_id, type, href) with insert_or_update only – old rows may survive.
10 | S04 | Existing page updated – a new link added | 1. BEFORE: run (b), note the count. 2. CC-1 → T0. 3. Edit Child AA → add sentence 'Go to Parent A' with a link to Parent A. Save/Publish. 4. Trigger (TP). | New page_dependency row for the new target; page updated; metadata.json lists new link; audit entry. | (a) SELECT dependency_page_id, type, relationship_label, relationship_confidence, relationship_reasoning, text, href, is_broken FROM page_dependency WHERE page_id = '43609' AND dependency_page_id = '43601'; (b) SELECT COUNT(*) AS links FROM page_dependency WHERE page_id = '43609'; (c) SELECT page_id, job_run_id, job_type, load_type, status, has_errors, error_details, revision, ingested_at FROM page_audit WHERE page_id IN ('43609') AND ingested_at > TIMESTAMP('<T0>') ORDER BY ingested_at; | (a) Exactly 1 row; type 'internal'; relationship_label one of: escalation, next_step, prerequisite, conditional_guidance, procedural_guidance; confidence 0–1; reasoning not empty; is_broken = false. (b) = before + 1. (c) 'completed'. | 43609 metadata.json Updated after T0 and contains 43601. |  | Not run
11 | S06 | Metadata-only change (title only, no body change) | 1. BEFORE: run (a) + (b), export. In GCS note crc32c hash of Child B page.md and page.html (Object details). 2. CC-1 → T0. 3. Rename Child B title to: Child B Renamed QA-ZX91 (do NOT edit the body). Save. 4. Trigger (TP). | Metadata columns update, content_size unchanged, links unchanged, page.md/page.html byte-identical, metadata.json updated. Check whether summary/tags churn unnecessarily. | (a) SELECT page_id, title, path, revision, content_size, date_modified, summary, ingested_at FROM page WHERE page_id = '43607'; (b) SELECT dependency_page_id, type FROM page_dependency WHERE page_id = '43607'; (c) Inbound links still valid: SELECT page_id, dependency_page_id, type, href, is_broken, is_redirect FROM page_dependency WHERE dependency_page_id = '43607'; (d) SELECT page_id, job_run_id, job_type, load_type, status, has_errors, error_details, revision, ingested_at FROM page_audit WHERE page_id IN ('43607') AND ingested_at > TIMESTAMP('<T0>') ORDER BY ingested_at; | (a) title = 'Child B Renamed QA-ZX91'; revision higher; content_size = before (if different, record – title may be inside the content); record whether path changed and whether summary changed. (b) Same as before. (c) Rows from Child AA, Child C, Parent B still point to 43607 with is_broken = false (record is_redirect). (d) 'completed'. | page.md / page.html crc32c = before (byte-identical). If different, record. metadata.json Updated after T0 with new title. |  | Not run |  | No partial re-tag path in code: re-tag always runs.
12 | S15 | Page containing multiple dependencies updated | 1. BEFORE: run (a), export (expect Child AA 43609, Child B 43607, Child C). 2. CC-1 → T0. 3. Edit QA Multi-Link S15: REMOVE link to Child AA, KEEP Child B and Child C, ADD link 'Parent B' → Parent B. Save. 4. Trigger (TP). | Existing dependency retained (no duplicate), removed one gone, new one created; metadata.json = current set. | (a) SELECT dependency_page_id, type, relationship_label, href, is_broken FROM page_dependency WHERE page_id = '<S15_ID>' ORDER BY dependency_page_id; (b) SELECT dependency_page_id, COUNT(*) AS n FROM page_dependency WHERE page_id = '<S15_ID>' GROUP BY dependency_page_id HAVING COUNT(*) > 1; (c) SELECT page_id, job_run_id, job_type, load_type, status, has_errors, error_details, revision, ingested_at FROM page_audit WHERE page_id IN ('<S15_ID>') AND ingested_at > TIMESTAMP('<T0>') ORDER BY ingested_at; | (a) Contains 43607, <CHILD_C_ID>, 43603; does NOT contain 43609 (if present → FAIL: stale dependency). (b) 0 rows. (c) 'completed'. | <S15_ID> metadata.json lists exactly 43607, <CHILD_C_ID>, 43603; page.md shows new link text. |  | Not run |  | Same stale-row risk as S03.
13 | S07 | Multiple rapid updates to the same page | 1. CC-1 → T0. 2. Within 2 minutes, edit Child C three times, saving each time: edit 1: add line 'QA-ZX91 rapid edit 1' edit 2: change it to 'QA-ZX91 rapid edit 2' edit 3: change it to 'QA-ZX91 rapid edit 3 FINAL' 3. Note final Athena revision Rf. 4. Trigger once (TP). Optional variant B: edit 1 → trigger → edits 2+3 → trigger. | Only the final state is persisted; no duplicate page/link rows; GCS has only the final version. | (a) SELECT page_id, revision, content_size, date_modified, ingested_at FROM page WHERE page_id = '<CHILD_C_ID>'; (b) SELECT dependency_page_id, type, COUNT(*) AS n FROM page_dependency WHERE page_id = '<CHILD_C_ID>' GROUP BY dependency_page_id, type HAVING COUNT(*) > 1; (c) SELECT page_id, job_run_id, job_type, load_type, status, has_errors, error_details, revision, ingested_at FROM page_audit WHERE page_id IN ('<CHILD_C_ID>') AND ingested_at > TIMESTAMP('<T0>') ORDER BY ingested_at; | (a) revision = Rf; ingested_at > T0. (b) 0 rows. (c) 'completed' rows only; no 'failed'. | Child C page.md contains 'rapid edit 3 FINAL' and does NOT contain 'rapid edit 1' / 'rapid edit 2'. |  | Not run
14 | S08 | Content reverted to a previous revision | 1. BEFORE: run (a) + (b), export. Note Parent B revision R0. 2. CC-1 → T0. 3. Edit Parent B: add sentence 'QA-ZX91 TEMPORARY S8 EDIT'. Save → revision R1. 4. Trigger (TP). Checkpoint: (a) shows R1. 5. CC-1 again → T1 (Run Log). 6. Parent B → Page history → select version R0 → Restore/Revert → Publish. Note new revision shown by Athena (R2). 7. Trigger (TP). | Final Spanner state matches the reverted content (not a mix); revisions history includes the intermediate edit; links = baseline; GCS = baseline. | (a) SELECT page_id, revision, revisions, content_size, date_modified, ingested_at FROM page WHERE page_id = '43603'; (b) SELECT dependency_page_id, type FROM page_dependency WHERE page_id = '43603' ORDER BY dependency_page_id; (c) Audit since T1: SELECT page_id, load_type, status, revision, ingested_at FROM page_audit WHERE page_id = '43603' AND ingested_at > TIMESTAMP('<T1>') ORDER BY ingested_at; | After step 7: (a) revision = R2 (Athena's latest); ingested_at > T1; content_size = R0 value; 'revisions' includes R1. (b) = before. (c) 'completed'. FAIL if revision is still R1 or page.md still contains 'TEMPORARY' → revert was skipped. | Parent B page.md does NOT contain 'TEMPORARY S8 EDIT' (Updated after T1). |  | Not run |  | Code skips a page if stored revision ≥ Athena revision. If Athena restores the OLD revision number, the revert is skipped → defect.
15 | S10 | Page moved to a different parent | 1. BEFORE: run (a) + (c), export. 2. CC-1 → T0. 3. Child C → Options → Move → destination Parent A → confirm. 4. Trigger (TP). | Single page row (same page_id), path updated; old parent's subpage link removed; new parent's subpage link added; no leftover GCS copy. | (a) SELECT page_id, title, path, revision, ingested_at FROM page WHERE page_id = '<CHILD_C_ID>'; (b) SELECT COUNT(*) AS n FROM page WHERE title = 'Child C'; (c) SELECT page_id, dependency_page_id, type FROM page_dependency WHERE dependency_page_id = '<CHILD_C_ID>' AND type = 'subpage'; (d) SELECT page_id, dependency_page_id, type, is_broken FROM page_dependency WHERE dependency_page_id = '<CHILD_C_ID>' AND type != 'subpage'; (e) SELECT page_id, job_run_id, job_type, load_type, status, has_errors, error_details, revision, ingested_at FROM page_audit WHERE page_id IN ('<CHILD_C_ID>', '43601', '43603') AND ingested_at > TIMESTAMP('<T0>') ORDER BY ingested_at; | (a) path ends /Test_Area/Parent_A/Child_C; same page_id; ingested_at > T0. (b) n = 1. (c) Exactly 1 row with page_id = 43601; NO row with page_id = 43603. (d) Inbound content links (e.g. from QA Multi-Link S15) still present, is_broken = false. (e) 'completed' for Child C and both parents. | Search each bucket for '<CHILD_C_ID>' → exactly one folder <FOLDER>/<CHILD_C_ID>/ with 3 objects Updated after T0. |  | Not run |  | 'failed_pages.json is clean' – ask dev where it lives on INT; mark N/A if not used.
16 | S14 | Hyperlink target page deleted | 1. BEFORE: run (b) – expect a row from Parent A (43601) → <S14_ID>. 2. CC-1 → T0. 3. Delete QA Link Target S14 (Options → Delete). Do NOT edit Parent A. 4. Trigger (TP). | Target page removed; its GCS files removed; links involving it cleaned (or flagged broken); Parent A stays valid; audit shows affected pages. | (a) SELECT COUNT(*) AS n FROM page WHERE page_id = '<S14_ID>'; (b) SELECT page_id, dependency_page_id, type, is_broken FROM page_dependency WHERE page_id = '<S14_ID>' OR dependency_page_id = '<S14_ID>'; (c) SELECT page_id, title, revision, ingested_at FROM page WHERE page_id = '43601'; (d) SELECT page_id, job_run_id, job_type, load_type, status, has_errors, error_details, revision, ingested_at FROM page_audit WHERE page_id IN ('<S14_ID>', '43601') AND ingested_at > TIMESTAMP('<T0>') ORDER BY ingested_at; (e) CC-6. | (a) n = 0. (b) No rows with page_id = <S14_ID>. Any remaining row 43601 → <S14_ID> must have is_broken = TRUE; is_broken = false → FAIL (stale relationship). (c) Parent A present. (d) Rows with load_type delete_page / purge_content for <S14_ID> and repair_inbound for 43601; status 'completed'. (e) 0 rows (or only is_broken = TRUE). | <FOLDER>/<S14_ID>/ absent in all 3 buckets. Parent A metadata.json Updated after T0 (link marked broken). |  | Not run |  | On 29-Sep is_broken was FALSE for all 4,776 rows – broken-link flagging may not be implemented.
17 | S05 | Page hard-removed from Athena | 1. BEFORE: run (b), export (expect subpage row Parent A → <S5_ID>). 2. CC-1 → T0. 3. Delete QA Delete Me S5 (Options → Delete). 4. Trigger (TP). | Page row removed; all its links removed (in- and outbound); GCS files removed; audit entries for the page and affected pages. | (a) SELECT COUNT(*) AS n FROM page WHERE page_id = '<S5_ID>'; (b) SELECT page_id, dependency_page_id, type FROM page_dependency WHERE page_id = '<S5_ID>' OR dependency_page_id = '<S5_ID>'; (c) SELECT page_id, job_run_id, job_type, load_type, status, has_errors, error_details, revision, ingested_at FROM page_audit WHERE page_id IN ('<S5_ID>', '43601') AND ingested_at > TIMESTAMP('<T0>') ORDER BY ingested_at; (d) Graph: GRAPH knowledge_graph MATCH (p:Page)-[d:DependsOn]->(t:Page) WHERE t.page_id = '<S5_ID>' RETURN p.page_id; | (a) n = 0. (b) 0 rows. (c) delete_page / purge_content rows for <S5_ID>, status 'completed'. (d) 0 rows. | <FOLDER>/<S5_ID>/ absent in all 3 buckets. |  | Not run |  | Deletes come from Athena /archive/pages and are only purged when GCS is available. If the page is still present after the run, ask dev whether archive processing is enabled.
18 | S09 | Page fails during processing (DEV-ASSISTED) | 1. Agree with dev: target page = Child B, and how the failure is induced for one run. 2. BEFORE: run (a) + (b), export. 3. CC-1 → T0. 4. Edit Child B body: add 'QA-ZX91 S9 edit'. Save. 5. Dev enables the failure. 6. Trigger (TP). | Pipeline fails gracefully at the correct stage, recorded in page_audit; baseline page/links/GCS unchanged; other pages unaffected. | (a) SELECT page_id, title, revision, content_size, ingested_at FROM page WHERE page_id = '43607'; (b) SELECT dependency_page_id, type FROM page_dependency WHERE page_id = '43607'; (c) SELECT page_id, job_run_id, job_type, load_type, status, has_errors, error_details, revision, ingested_at FROM page_audit WHERE page_id IN ('43607') AND ingested_at > TIMESTAMP('<T0>') ORDER BY ingested_at; (d) SELECT page_id, job_run_id, status, watermark_time, ingested_at FROM page_since WHERE page_id = '39960' ORDER BY ingested_at DESC LIMIT 3; | (a) = before (old revision, ingested_at < T0). (b) = before. (c) ≥ 1 row status 'failed', has_errors = true, error_details names the stage (fetch / markdown / metadata). (d) Record: code says a failed page blocks its root's watermark from advancing. | Child B objects Updated BEFORE T0 (unchanged). |  | Not run |  | Cannot be forced by QA alone on INT. Mark Blocked if dev support unavailable.
19 | S16 | Previously failed page successfully reprocessed | 1. Continue straight after S09 (keep the S9 edit). 2. Dev removes the failure. 3. CC-1 → T1. 4. Trigger (TP). | Page processed on retry; correct state persisted; links correct; GCS complete; failure does not permanently block; audit shows failure then success. | (a) SELECT page_id, revision, content_size, ingested_at FROM page WHERE page_id = '43607'; (b) Full history since S09 T0: SELECT page_id, job_run_id, load_type, status, has_errors, ingested_at FROM page_audit WHERE page_id = '43607' AND ingested_at > TIMESTAMP('<T0 of S09>') ORDER BY ingested_at; (c) SELECT page_id, status, watermark_time, ingested_at FROM page_since WHERE page_id = '39960' ORDER BY ingested_at DESC LIMIT 3; (d) SELECT dependency_page_id, type FROM page_dependency WHERE page_id = '43607'; | (a) revision = Athena latest; ingested_at > T1. (b) 'failed' row(s) from S09 followed by 'completed' row(s). (c) New COMPLETED row after T1 with watermark_time advanced. (d) Same links as SU-3 baseline. | Child B page.md contains 'S9 edit'; all 3 objects Updated after T1. |  | Not run

## Run Log
Case ID | Date | Tester | T0 (UTC, from CC-1) | T1 (if used) | Trigger (Bruno / Scheduler) | job_id (Bruno) | job_run_id (CC-2) | Athena revision before | Athena revision after | Notes
EXAMPLE | 01-Oct-2026 | Vamsi | 2026-10-01T09:15:02.123456Z |  | Bruno | 8f2c… | 2c6927dd20a04dc2ab349815cb5b9ab9 | 4 | 5 | Example row – delete when starting.
SU-1
SU-2
SU-3
S12
S13
S11
S01
S02
S03
S04
S06
S15
S07
S08
S10
S14
S05
S09
S16

## Defects & Observations
ID | Case | Type | Summary | Evidence | Expected | Actual | Severity | Jira key | Status
PRE-1 | SU-1 | Blocker (env) | INT Spanner schema older than repo DDL: no 'job' table; page_audit has no 'job_type'; page has 'is_draft' not 'draft_state'. | Discovery 29-Sep (information_schema) | Schema = Liquibase 20260903_0900 changeset | Old schema | High |  | Open – confirm with dev
PRE-2 | SU-1 | Observation | No pipeline run on INT since 18-Sep-2026 15:14 UTC; Test Area pages last ingested 14-Sep – Spanner does not match Athena. | page_since / page queries 29-Sep | Runs every 30 min | No runs | High |  | Open – confirm with dev
PRE-3 | S14 | Observation | is_broken = FALSE for all 4,776 page_dependency rows – broken-link flagging may not be implemented. | COUNTIF(is_broken) = 0 | Broken links flagged | Never flagged | Medium |  | Open – confirm with dev
PRE-4 | - | Observation | Root 39963 page_since rows have NULL since_time / watermark_time while status = COMPLETED. | page_since query 29-Sep | Watermark populated | NULL | Medium |  | Open – confirm with dev
PRE-5 | PF-8 | Observation | page_audit table is EMPTY on INT. | GROUP BY load_type,status returned no rows | Audit rows per processed page | 0 rows | Medium |  | Open – recheck after deployment
PRE-6 | - | Observation | Leaf pages (Child A/AA/B) have page_type 'Parent'; parents have 'Navigation'. Confirm intended semantics. | Test Area query 29-Sep | - | - | Low |  | Open – confirm with dev

## Summary
Status | Count
Pass | 0
Pass with observation | 0
Fail | 0
Blocked | 0
Not run | 16
Total scenarios | 16
Executed % | 0%
Note | Counts the 16 scenarios on 'Test Cases' (setup rows SU-1..SU-3 excluded).